## How to use
Event Load-In Schedule
Plan when every vendor arrives, where they unload, and when setup has to be finished. Works for weddings, corporate events, conferences, festivals, trade shows, and galas.
QUICK START
1 | Fill in Event Info | Event name, date, venue, and key times. They flow into the Schedule and Call Sheet automatically.
2 | Add your logo | On the Schedule tab, click the "Your logo here" box, then Insert > Picture and drag your logo over it.
3 | Replace the examples | Type over the 8 sample vendors (or clear them) and add your own. White cells are for typing. Blue-gray cells calculate on their own, so leave those alone.
4 | Check the flags | Red or orange cells point at problems: a setup that runs into doors, a vendor arriving before the venue opens, or two vendors at the same dock at the same time.
5 | Send it out | Share the Schedule (PDF or link) with the venue and every vendor about a week before. Confirm windows the day before and update the Status column.
6 | Print the Call Sheet | It lists every vendor in arrival order with contact, phone, and entrance. Clipboard ready.
TIPS FOR A SMOOTH LOAD-IN
✓ | Order arrivals by dependency | Rentals, tent, staging, and power go first. Florals and decor once tables are set. Catering, cake, and entertainment last.
✓ | Use windows, not exact times | A 30 to 60 minute window is realistic with traffic and parking. The template plans around the end of the window, so you see the latest likely finish.
✓ | Give every vendor an entrance | Naming the dock or door keeps vans from stacking up out front, and lets the Dock check spot overlaps.
✓ | Protect a buffer before doors | Aim for setup to wrap 30 to 60 minutes before guests arrive, so there is time for a walkthrough and a final sweep.
✓ | Send a week out, confirm the day before | A quick text to each vendor the day before catches most surprises.
✓ | Plan the load-out too | Venues often charge for overtime. Set a load-out deadline and share it with everyone.
WHAT THE CALCULATED COLUMNS MEAN
| Setup complete by | End of the arrival window plus setup time (minutes).
| Buffer before doors | Time between that finish and guest arrival. Red if it runs past doors, orange if it is under your minimum buffer (set on Event Info).
| Dock check | "Overlap" when two vendors share an entrance with overlapping windows. Fine for a big loading area, worth a second look for a single dock.
| Summary tiles | Vendor count, confirmations, first arrival, last setup, buffer to doors, and flags.
STATUS COLORS
| Not confirmed | Sent, but the vendor has not confirmed their window yet.
| Confirmed | Vendor confirmed the window, entrance, and setup time.
| On the way | Event day: vendor is driving in.
| Arrived | Event day: vendor is on site and unloading.
| Setup complete | Event day: done and out of the way.
GOOD TO KNOW
· | All times are for one day (load-in through load-out before midnight). Put overnight load-outs in Notes.
· | Room for 38 vendors. Need more? Insert rows inside the table and copy a filled row down so the formulas come along. The Call Sheet lists the first 38.
· | Works in Microsoft Excel, Google Sheets (File > Import), and Apple Numbers. No macros. Nothing is locked.
· | Hidden helper columns on the Schedule power the Call Sheet. Leave them in place.
On event day, track live vendor ETAs with ETA Tracker: send each vendor a link, see who's on the way, running late, or arrived. etatracker.io
Made with ETA Tracker · etatracker.io

## Event Info
Event Info
Fill this in first. Everything here flows into the Schedule and the Call Sheet. White boxes are for typing; blue-gray boxes calculate on their own.
EVENT
Event name | Spring Celebration Gala | Shows at the top of the Schedule and Call Sheet.
Event date | 2027-05-15 | Type it as a date, for example 5/15/2027.
Event type | Gala / fundraiser | Optional. Pick from the list or type your own.
VENUE
Venue name | The Foundry Hall
Venue address | 415 Riverside Drive, Springfield | Vendors will look for this, so include the city.
TIMELINE (ALL TIMES ON THE EVENT DAY)
Load-in access opens | 7:00 | Earliest a vendor can get in. Arrivals before this get flagged.
Guest arrival / doors | 18:00 | Every setup is measured against this time.
Event ends | 22:00
Load-out deadline | 23:30 | Latest the venue allows. Later load-outs get flagged.
Minimum buffer before doors | 30 | Setups that finish closer to doors than this are flagged orange. 30 to 60 is typical.
Load-in window (auto) |  | Time between access opening and doors.
CONTACTS
Planner / lead name | Jordan Ellis | Appears on the Call Sheet.
Planner phone | (555) 010-2040
Venue contact name | Priya Shah, venue manager
Venue contact phone | (555) 010-3355
NOTES FOR VENDORS
Vendor parking on Riverside Drive, not the guest lot. Freight elevator runs 7:00 AM to 11:30 PM. Certificates of insurance (COI) due from every vendor by May 1. No open flame inside. Venue Wi-Fi: FoundryGuest.
Parking, freight elevator hours, insurance (COI) deadlines, venue rules, Wi-Fi.

## Schedule
YOUR LOGO HERE Insert > Picture, then drag your logo over this box |  |  | LOAD-IN SCHEDULE | [7 empty] | Load-in access opens
Guest arrival / doors
Event ends
Load-out deadline
Minimum buffer
Edit these on the Event Info tab
VENDORS |  |  | CONFIRMED |  | FIRST ARRIVAL |  |  | LAST SETUP DONE |  |  | BUFFER TO DOORS |  |  | FLAGS TO REVIEW
[5 empty] | ARRIVAL WINDOW |  |  |  | CALCULATED FOR YOU
# | Vendor / company | Category | Day-of contact | Phone | From | To | Entrance / dock | Setup time (min) | Setup complete by | Buffer before doors | Dock check | Load-out | Status | Notes | Sort key | Buffer min
| Summit Party Rentals | Rentals | Dana Ruiz | (555) 010-0142 | 7:00 | 7:30 | Loading dock A | 120 |  |  |  | 23:00 | Confirmed | Tables, chairs, linens. Dock A must be clear by 7:00 AM.
| Brightline Staging & Lighting | Lighting | Marcus Webb | (555) 010-0178 | 8:00 | 8:30 | Loading dock A | 180 |  |  |  | 22:30 | Confirmed | Stage, truss, uplights. Needs 2 x 20A circuits by the stage.
| Echo AV Productions | AV / Sound | Lena Park | (555) 010-0193 | 9:00 | 9:30 | Loading dock A | 150 |  |  |  | 22:30 | Confirmed | Sound check 3:00 PM with the band. Projector for slideshow.
| Wildflower Studio | Florist | Ava Thompson | (555) 010-0127 | 11:00 | 11:30 | Courtyard gate | 180 |  |  |  | 22:15 | Confirmed | Centerpieces go out after linens are set.
| Harvest Table Catering | Catering | Chef Omar Haddad | (555) 010-0165 | 13:00 | 13:30 | Kitchen service door | 210 |  |  |  | 22:30 | Confirmed | Hot boxes plus freight elevator. 180 guests, 3 dietary lists.
| Night Owl DJ & Sound | Entertainment / DJ / Band | Chris Nolan | (555) 010-0110 | 15:00 | 15:45 | Loading dock A | 120 |  |  |  | 22:15 | Not confirmed | Confirm arrival window. Setup needs the stage clear.
| Sweet Layers Bakery | Cake / Desserts | Mia Chen | (555) 010-0136 | 15:30 | 16:00 | Loading dock A | 45 |  |  |  | 20:30 | Confirmed | Cake table by the dance floor. Needs a cart.
| Golden Hour Photo | Photo / Video | Sam Rivera | (555) 010-0151 | 16:30 | 16:45 | Main lobby | 30 |  |  |  | 22:00 | Not confirmed | Detail shots of the room before doors open.
How to read the flags: Red means setup finishes after doors, the window is backwards, or load-out runs past the deadline. Orange means less buffer than your minimum, an arrival before access opens, or two vendors at the same entrance at overlapping times. Setup complete by = end of window + setup time.
|  | Made with ETA Tracker · etatracker.io | [11 empty] | Free template. Copy, edit, and share it.

## Call Sheet
DAY-OF CALL SHEET |  |  |  |  | PLANNER
VENUE
ACCESS / DOORS
LOAD-OUT BY
ARRIVAL WINDOW
# | From | To | Vendor | Category | Contact | Phone | Entrance / dock | Arrived | Notes | Row
Pulled from the Schedule tab and ordered by arrival. Edit vendors there, not here. Print this page for your clipboard and tick vendors off as they arrive.